## Read me
MAS migration test plan
Companion to the guide at https://autotestx.com/guides/mas-migration-testing-plan
What is in this workbook:
1. Baseline: your critical workflows run on the current Maximo before anything changes, with their result and evidence.
2. Workflow comparison: the same workflows on MAS, side by side with the baseline, and what each difference is.
3. Integrations: every interface, how it authenticates today and on MAS, and how it is tested.
4. Customizations: scripts, Java classes, configuration and reports, and how each is verified.
5. Issue log: every difference that needs action, with an owner and a retest.
6. Exit criteria: what has to be true before cutover.
How to classify a difference (sheet 2):
Expected change: MAS behaves differently by design (a new sign-in page, a renamed button). Update the test, not the system.
Defect: the business outcome is wrong (wrong status, wrong cost, a missing record). Log it.
Test update: the test can no longer find something that still works. Fix the test.
Data: the record the test needs doesn't exist or is in another state on MAS. Fix the data.
Environment: MAS can't be reached, a service is down, a certificate is wrong. Fix the environment.
Already failing: it failed in the baseline too. Not a migration issue; keep its existing ticket.

## 1. Baseline
ID | Workflow | Baseline result | Run date | Version | Evidence (link) | Notes
WM-01 | Create, approve and complete a corrective work order | Passed |  | Maximo 7.6.1.3
PU-01 | Purchase requisition to approved purchase order | Passed |  | Maximo 7.6.1.3
PU-03 | Match an invoice to a received purchase order | Failed |  | Maximo 7.6.1.3 |  | Known: tolerance message, ticket 4411

## 2. Workflow comparison
ID | Workflow | Baseline | On MAS | What differs | Classification | Issue # | Retest result
WM-01 | Create, approve and complete a corrective work order | Passed | Failed | Sign-in page is MAS's own; the test stopped at sign-in | Expected change
PU-01 | Purchase requisition to approved purchase order | Passed | Failed | PO status stays WAPPR: workflow did not route to the approver | Defect | MAS-007
PU-03 | Match an invoice to a received purchase order | Failed | Failed | Same tolerance message as the baseline | Already failing | 4411

## 3. Integrations
Integration | Direction | Mechanism | Auth today | Auth on MAS | How it is tested | Owner | Status
Work orders to finance | Outbound | Publish channel (MIF) |  |  | Approve a WO; check the message reaches the endpoint; check the error queue is empty |  | Not started
Purchase orders from ERP | Inbound | REST / OSLC API | Basic (maxauth) | API key | Send a sample PO; check it exists in Maximo with the right lines and status |  | Not started
Meter readings from SCADA | Inbound | Flat file / cron task |  |  | Drop a sample file; check the readings on the asset; check the rejected file is empty |  | Not started

## 4. Customizations
Item | Type | Where it acts | Workflow that proves it (ID) | Migration note | Status
Default the work type from the asset | Automation script | WORKORDER save | WM-01 | Scripts move with the database; verify behaviour | Not started
PO approval limit by group | Workflow process | PO status change | PU-01 | Check routing and assignments | Not started
Custom field validation class | Java class | Field validation on ASSET | AS-01 | Java customizations must be packaged for MAS; confirm with your partner | Not started
Work order cost report | BIRT report | Work Order Tracking |  | Run with the same parameters on both; compare totals | Not started

## 5. Issue log
Issue # | Found in (ID) | Summary | Classification | Severity | Owner | Fixed in | Retest | Closed
MAS-007 | PU-01 | PO approval workflow does not route to the purchasing manager | Defect | High

## Checklist
Check | Done
Every Smoke and Core workflow has run on MAS, and every difference is classified.
No open Defect of Critical or High severity, or each one has an accepted workaround, signed off.
Every integration has passed end to end on MAS with a real payload, including its error path.
Every customization in sheet 4 has a workflow that proves it, and that workflow passed.
Security: each test user role signed in through the MAS sign-in and saw only what it should.
Reports in daily use return the same totals as the baseline for the same parameters.
Tests updated for expected changes are re-run, so the regression suite is ready for production.
A Smoke run is planned for straight after cutover, and someone is named to read it.